## Catalog Sprint Plan
Task ID | Phase | Task | Assignee | Size | Priority | Status | Day (1-10) | Depends On | Notes
1.1 | Phase 1 | Wire getProcessCatalogRows → GET /api/process-catalog/rows | Dev 1 | S | P0 | Not Started | 1 |  | Replace mock in processCatalogService.ts
1.2 | Phase 1 | Wire getGroupCompanies → GET /api/group-companies | Dev 1 | S | P0 | Not Started | 1 |  | Replace mock in processCatalogService.ts
1.3 | Phase 1 | Wire getLevel4ByParent → GET /api/level4?parentId= | Dev 1 | S | P0 | Not Started | 1-2 |  | Replace mock in level4Service.ts
1.4 | Phase 1 | Wire getMyTasks → GET /api/process-catalog/my-tasks | Dev 2 | S | P0 | Not Started | 1 |  | Replace mock in processCatalogService.ts
1.5 | Phase 1 | Wire getSubmittedRequests → GET /api/process-catalog/submitted-requests | Dev 2 | S | P0 | Not Started | 1 |  | Replace mock in processCatalogService.ts
1.6 | Phase 1 | Wire RecordedChangesPage → GET /api/process-catalog/recorded-changes | Dev 2 | M | P1 | Not Started | 2 |  | Currently fully mocked in RecordedChangesPage.tsx
1.7 | Phase 1 | Add error states & loading skeletons to all query consumers | Dev 1 | M | P1 | Not Started | 2 | 1.1-1.3 | CatalogModule, tabs, RecordedChangesPage
1.8 | Phase 1 | Verify pagination params passed & handled correctly | Dev 2 | S | P1 | Not Started | 2 | 1.4-1.5 | Check useGetProcessCatalogRows + all hooks
2.1 | Phase 2 | Create useAddProcess mutation hook (POST /api/process-catalog) | Dev 1 | M | P0 | Not Started | 3 |  | New file in hooks/
2.2 | Phase 2 | Wire AddProcessesModal submit → useAddProcess | Dev 1 | S | P0 | Not Started | 3-4 | 2.1 | Replace console.log in AddProcessesModal.tsx
2.3 | Phase 2 | Create useAddLevel4 mutation hook (POST /api/level4) | Dev 2 | M | P0 | Not Started | 3 |  | New file in hooks/
2.4 | Phase 2 | Wire AddLevel4sModal submit → useAddLevel4 + cache invalidation | Dev 2 | S | P0 | Not Started | 3-4 | 2.3 | Replace placeholder in CatalogModule.tsx:504
2.5 | Phase 2 | Create useEditLevel4 mutation hook (PUT /api/level4/:id) | Dev 2 | M | P0 | Not Started | 4 |  | New file in hooks/
2.6 | Phase 2 | Wire EditLevel4sModal submit → useEditLevel4 | Dev 2 | S | P0 | Not Started | 4-5 | 2.5 | Replace placeholder in CatalogModule.tsx:543
2.7 | Phase 2 | Create useRenameProcess mutation hook (PATCH /api/process-catalog/:id/rename) | Dev 1 | S | P1 | Not Started | 4 |  | New file in hooks/
2.8 | Phase 2 | Wire RenameModal submit → useRenameProcess | Dev 1 | S | P1 | Not Started | 4-5 | 2.7 | Wire in RenameModal.tsx
2.9 | Phase 2 | Implement bulk entity toggle (PATCH /api/process-catalog/entities) | Dev 1 | M | P1 | Not Started | 5 |  | Batch update for entity checkboxes
2.10 | Phase 2 | Implement validate action (replace placeholder at CatalogModule:339) | Dev 2 | M | P1 | Not Started | 5 |  | Wire to backend validation endpoint
2.11 | Phase 2 | Add success/error toast notifications for all mutations | Dev 2 | S | P1 | Not Started | 5-6 | 2.4,2.6 | Consistent UX across all write ops
3.1 | Phase 3 | Wire 'Go to affected record' in RequestDetailsSheet | Dev 1 | S | P1 | Not Started | 6 |  | Currently no handler in RequestDetailsSheet.tsx
3.2 | Phase 3 | Wire task deep-link navigation (navigateToProcess in store) | Dev 1 | S | P1 | Not Started | 6 |  | useCatalogNavStore.ts
3.3 | Phase 3 | Implement row-level context menu actions (delete, duplicate, move) | Dev 2 | M | P2 | Not Started | 6-7 |  | New context menu + mutation hooks
3.4 | Phase 3 | Handle tab fallback view (replace placeholder at CatalogModule:446) | Dev 2 | S | P2 | Not Started | 7 |  | Proper empty/error state
4.1 | Phase 4 | Add empty-state UI for zero-result tables (catalog, tasks, requests) | Dev 1 | S | P1 | Not Started | 7 |  | NoTasks-style component for each table
4.2 | Phase 4 | Handle API error responses gracefully in all query hooks | Dev 1 | M | P1 | Not Started | 7-8 |  | Retry logic, error boundaries
4.3 | Phase 4 | Verify status filter values match API ProcessStatus enum | Dev 2 | S | P1 | Not Started | 7 |  | catalog-columns.tsx vs API enum casing
4.4 | Phase 4 | Verify export-to-Excel works with real data + large datasets | Dev 1 | M | P2 | Not Started | 8 | 1.1,1.3 | exportToExcel.ts uses level4Service
4.5 | Phase 4 | Remove all mock data imports from production code paths | Dev 2 | S | P0 | Not Started | 8 | 2.1-2.10 | Clean up mock-data.ts references
4.6 | Phase 4 | Keyboard accessibility audit for modals & filter sheet | Dev 2 | M | P2 | Not Started | 8-9 |  | Focus traps, tab order, aria labels
4.7 | Phase 4 | End-to-end smoke test: full flow with real APIs | Both | L | P0 | Not Started | 9-10 | All | Manual QA pass on all features

## Sprint Summary
Metric | Value
Module | Process Catalog
Sprint Duration | 2 weeks (10 working days)
Team Size | 2 developers
Total Tasks | 30
Phase 1 — API Integration (Read) | 8 tasks → Days 1-2
Phase 2 — Mutations (Write) | 11 tasks → Days 3-6
Phase 3 — Actions & Navigation | 4 tasks → Days 6-7
Phase 4 — Polish & Edge Cases | 7 tasks → Days 7-10
Key Dependencies | Backend APIs must be deployed to dev
Blocker Risk | Some APIs still not added yet may we need it
Testing | Excluded from this sprint (next sprint)

## Day-by-Day Plan
Day | Dev 1 | Dev 2
Day 1 | 1.1 Wire catalog rows API 1.2 Wire group companies API | 1.4 Wire my-tasks API 1.5 Wire submitted-requests API
Day 2 | 1.3 Wire level4 API 1.7 Error states & loading skeletons | 1.6 Wire recorded changes API 1.8 Verify pagination
Day 3 | 2.1 Create useAddProcess hook 2.2 Wire AddProcessesModal | 2.3 Create useAddLevel4 hook 2.4 Wire AddLevel4sModal
Day 4 | 2.7 Create useRenameProcess hook 2.8 Wire RenameModal | 2.5 Create useEditLevel4 hook 2.6 Wire EditLevel4sModal
Day 5 | 2.9 Bulk entity toggle update | 2.10 Implement validate action 2.11 Toast notifications
Day 6 | 3.1 Wire 'Go to affected record' 3.2 Task deep-link navigation | 3.3 Row-level context menu actions
Day 7 | 4.1 Empty-state UI for tables 4.2 API error handling | 3.4 Tab fallback view 4.3 Verify status filter values
Day 8 | 4.4 Verify Excel export with real data | 4.5 Remove mock data imports 4.6 Accessibility audit
Day 9 | 4.7 E2E smoke test (part 1) | 4.7 E2E smoke test (part 1)
Day 10 | 4.7 E2E smoke test (part 2) + fix found issues | 4.7 E2E smoke test (part 2) + fix found issues